## TASK
task_code | status_code | wbs_id | task_name | start_date | end_date | resource_list | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Start | (*)Finish | (*)Resources | Delete This Row
A1000 | Not Started | WT-101.1 | Project Start | 2021-01-31 | 2021-02-04 18:00
A1010 | Not Started | WT-101.1 | Project Moblization | 2021-01-31 | 2021-02-04 18:00
A1020 | Not Started | WT-101.1 | Primary Works to Start Project | 2021-01-31 | 2021-02-04 18:00
A1030 | Not Started | WT-101.2 | Cleaning and Grabing of Site | 2021-01-31 | 2021-02-04 18:00
A1040 | Not Started | WT-101.3 | Site Survey Work | 2021-01-31 | 2021-02-04 18:00
A1050 | Not Started | WT-101.4 | Excavation Work | 2021-01-31 | 2021-02-04 18:00
A1060 | Not Started | WT-101.5 | P.C.C Work | 2021-01-31 | 2021-02-04 18:00
A1070 | Not Started | WT-101.6 | Raft Foundation Work | 2021-01-31 | 2021-02-04 18:00
A1080 | Not Started | WT-101.7 | Column Concrete Work | 2021-01-31 | 2021-02-04 18:00
A1090 | Not Started | WT-101.8 | Shear Wall Concrete Work | 2021-01-31 | 2021-02-04 18:00
A1100 | Not Started | WT-101.9 | MEP Fiiting in Walls | 2021-01-31 | 2021-02-04 18:00
A1110 | Not Started | WT-101.10 | Water Tank Slab Concrete | 2021-01-31 | 2021-02-04 18:00
A1120 | Not Started | WT-101.11 | Backfliing Work | 2021-01-31 | 2021-02-04 18:00

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=-1 SmallScaleQtyType=QT_Hour DateFormat=dd/MM/yyyy CurrencyFormat=US Dollar