## BOUNDRAY WALL PROJECT
PLANNING-P6 PROCUREMENT TRACKING SHEET/LEDGER/REGISTER/DIARY
S# | Description | Unit | Qty | Required as Per Schedule | Preparation & Approval of Specification | Issuance of RFQ | Evaluation of Proposal | Finalization of Supplier / Vendor | PO issued | Plan delivery date | Actual Delivery at Site | Quantity Received At Site | Balance Material | Lead Time | Remarks
Civil Material / Construction Material
1 | Bircks /Stone | CFT | 300 | 2023-01-31 | In-Progress | [8 empty] | 30 Days
2 | Sand | CFT | 600 | 2023-02-07 | [10 empty] | At least 100 CFT on 7-Feb-23
3 | Crush
4 | Cement (1Shipment)
5 | Steel
6 | Formwork Material
7 | Bricks
8
9
10
Legends:
Remaining
Please RE Check in PO
Added / Revised
Received / Completed
Not Required / Deleted
Available
Hold

## Sheet1
PLANNING-P6 PROCUREMENT TRACKING SHEET/LEDGER/REGISTER/DIARY
S# | Description | Unit | Qty | Preparation & Approval of Specification | Issuance of RFQ | Evaluation of Proposal | Finalization of Supplier / Vendor | PO issued | Plan delivery date | Actual Delivery at Site | Quantity Received At Site | Balance Material | Lead Time | Remarks
Mechanical
A | Surface Piping
1 | Pipes
1.1 | Dia.3" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A30-05 | Meter | 399.8 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 396 | 3.8
1.2 | Dia. 2" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH80 P01A01-A30-07 | Meter | 746 | Done | Done | Done | Done | Done | 2018-08-20 | 21-Oct-18 6-Dec-18 | 714 | 32
1.3 | Dia. 1 1/2" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH80 P01A01-A32-07 | Meter | 4.3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -1.7
1.4 | Dia. 1" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH80 P01A01-A32-07 | Meter | 4.6 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -1.4
1.5 | Dia. 3/4" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH80 P01A01-A32-07 | Meter | 1.3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 11 | -9.7
1.6 | Dia. 1/2" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH80 P01A01-A32-07 | Meter | 0.9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -5.1
1.7 | Dia. 4" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A31-05 | Meter | 138 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 131.6 | 6.4
1.8 | Dia. 1" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH160 P01A01-A32-11 | Meter | 2.2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -3.8
1.9 | Dia. 3/4" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH160 P01A01-A32-11 | Meter | 3.6 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -2.4
1.1 | Dia. 1/2" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH160 P01A01-A32-11 | Meter | 0.2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | -5.8
1.11 | Dia.1" ASTM A106 GR.B GALVANIZED SMLS NPT ASMEB36.10M SCH80 P01A01-F12-07 | Meter | 94.2 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 94.2
1.12 | Dia.3/4" ASTM A106 GR.B GALVANIZED SMLS NPT ASMEB36.10M SCH80 P01A01-F12-07 | Meter | 13.2 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 13.2
2 | Elbow 90
2.1 | Dia. 3" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASMEB16.9 SCH40 P02A01-A01-05 | NOS | 17 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 17 | 0
2.2 | Dia. 2" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASMEB16.9 SCH80 P02A01-A01-07 | NOS | 68 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-12-06 | 68 | 0
2.3 | Dia. 1 1/2" ASTM A105 CL3000 SW ASME-B16.11 P02B11-A01 | NOS | 6 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | 0
2.4 | Dia. 1" ASTM A105 CL3000 SW ASME-B16.11 P02B11-A01 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
2.5 | Dia. 4" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASMEB16.9 SCH40 P02A01-A01-05 | NOS | 11 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 11 | 0
2.6 | Dia. 3/4" ASTM A105 CL3000 SW ASME-B16.11 P02B11-A01 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 6
2.7 | Dia. 1" ASTM A105 GALVANIZED CL3000 NPT ASME-B16.11 P02B11-A04 | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 1 | 0
2.8 | Dia. 3/4" ASTM A105 GALVANIZED CL3000 NPT ASME-B16.11 P02B11-A04 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 0
3 | Elbow 45 | [10 empty] | 0
3.1 | Dia. 3" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASMEB16.9 SCH40 P03A01-A01-05 | NOS | 8 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 8 | 0
3.2 | Dia. 4" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASMEB16.9 SCH40 P03A01-A01-05 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 8 | -4
4 | EQUAL TEE
4.1 | Dia. 3" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 P04A01-A01-05 | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 5 | 0
4.2 | Dia. 2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH80 P04A01-A01-07 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
4.3 | Dia. 4" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 P04A01-A01-05 | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 5 | 0
4.4 | Dia. 2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH80 P04A01-A01-07 | NOS | 30 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 30 | 0
4.5 | Dia 1" ASTM A105 GALVANIZED CL3000 NPT ASME-B16.11 P04B11-A04 | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 1 | 0
5 | REDUCING TEE
5.1 | Dia. 3"x2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 (L) X SCH80 (S) P05A01-A01-0507 | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 1 | 0
5.2 | Dia. 3/4"x1/2" ASTM A105 CL3000 SW ASME-B16.11 P05B11-A01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
5.3 | Dia. 4"x2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 (L) X SCH80 (S) P05A01-A01-0507 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 21-Oct-18 6-Dec-18 | 3 | 1
5.4 | Dia. 1"x3/4" ASTM A105 GALVANIZED CL3000 NPT ASME-B16.11 P05B11-A04 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 0
6 | SWAGED NIPPLE:
6.1 | Dia. 2"x1" ASTM A105 BE(L)-PE(S) L=120MM SCH80 (L) X SCH80 (S) P10A00-D01-0707 | NOS | 6 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | 0
6.2 | Dia. 2"x1 1/4" ASTM A105 BE(L)-PE(S) L=120MM SCH80 (L) X SCH80 (S) P10A00-D01-0707 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
6.3 | Dia. 3/4"x1/2" ASTM A105 PE(L)-PE(S) L=120MM SCH80 (L) X SCH80 (S) P10A00-D02-0707 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
6.4 | Dia. 2"x1" ASTM A105 BE(L)-PE(S) L=120MM SCH80 (L) X SCH160 (S) P10A00-D01-0711 | NOS | 6 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 6 | 0
7 | CONCENTRIC REDUCER
7.1 | Dia. 3"x2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 (L) X SCH80 (S) P06A01-A01-0507 | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 5 | 0
8 | EECENTRIC REDUCER
8.1 | Dia. 4"x2" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 (L) X SCH80 (S) P07A01-A01-0507 | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 5 | 0
9 | SOCKOLET
9.1 | Dia. 3"x1 1/2" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | -2
9.2 | Dia. 3"x1 " ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | -2
9.3 | Dia. 3"x3/4" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 41 | -39
9.4 | Dia. 3"x1/2" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 7 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 9 | -2
9.5 | Dia. 2"x3/4" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 9
9.6 | Dia. 4"x3/4" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 8 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 8
9.7 | Dia. 4"x1/2" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 2
9.8 | Dia. 2"x1 1/2" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 2
9.9 | Dia. 2"x1" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 2
9.1 | Dia. 2"x3/4" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11-D01 | NOS | 19 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 |  | 19
10 | BALL VALVE
10.1 | Dia. 3" BODY:ASTM A216 GR.WCB TRIM/BALL:13%CR FLOATING BALL REIN-PTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL150 WRENCH OPERATED FLANGED RF ASME B16.34 P33B1B-D09 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-12-06 | 5 | -2
10.2 | Dia. 2" BODY:ASTM A216 GR.WCB TRIM/BALL:13%CR FLOATING BALL REIN-PTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL150 WRENCH OPERATED FLANGED RF ASME B16.34 P33B1B-D09 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-12-06 | 3 | 0
10.3 | Dia. 1" BODY:ASTM A216 GR.WCB TRIM/BALL:13%CR FLOATING BALL REIN-PTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL150 WRENCH OPERATED FLANGED RF ASME B16.34 P33B1B-D01 | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 1 | 0
10.4 | Dia. 3/4" BODY:ASTM A105 TRIM/BALL:13%CR FLOATING BALL REINPTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL800 WRENCH OPERATED SW-NPT BS 5351 P33B1H-D02 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 9
10.5 | Dia.4" BODY: ASTM A216 GR WCB, BALL/TRIM: TP316L FLOATING BALL STRG: REIN-PTFE ANTISTATIC FIRESAFE BS 6755 CL150 WRENCH OPERATED FLANGED RF ASME B16.34 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 0
10.6 | Dia.2" BODY: ASTM A216 GR WCB, BALL/TRIM: TP316L FLOATING BALL STRG: REIN-PTFE ANTISTATIC FIRESAFE BS 6755 CL150 WRENCH OPERATED FLANGED RF ASME B16.34 P33B1B-D12 | NOS | 21 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-12-06 | 15 | 6
10.7 | Dia.1" BODY: ASTM A216 GR WCB, BALL/TRIM: TP316L FLOATING BALL STRG: REIN-PTFE ANTISTATIC FIRESAFE BS 6755 CL150 WRENCH OPERATED FLANGED RF ASME B16.34 P33B1B-D07 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
10.8 | Dia. 3/4" BODY:ASTM A105 TRIM/BALL:TP 316L FLOATING BALL REINPTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL800 WRENCH OPERATED SW-NPT BS 5351 P33B1H-D06 | NOS | 27 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 27
10.9 | Dia. 3/4" BODY:ASTM A105 TRIM/BALL:13%CR FLOATING BALL REINPTFE ANTISTATIC FIRESAFE BS6755 END ENTRY CL800 WRENCH OPERATED NPT BS 5351 P33B1H-D03 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 3
11 | GATE VALVE
11.1 | Dia. 1/2" BODY: ASTM A105 TRIM:13% CR D&S: STL CL800 BBBGOS& Y STD-PORT SW-NPT API602 P30B1H-A12 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 3
12 | CHECK VALVE
12.1 | Dia. 2" BODY: ASTM A216 GR.WCB TRIM:316L D&S: STL CL150 SWING CHECK TYPE BOLTED COVER FLANGED RF API 600 P32C1B-D03 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 9 | 0
13 | PCV
13.1 | Dia. 1" PRESSURE CONTROL VALVE. | NOS | 6 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 6
14 | PSV
14.1 | Dia. 1"x1" THERMAL SAFETY VALVE | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 1
15 | PSV
15.1 | Dia. 1"x1" PRESSURE SAFETY VALVE. | NOS | 1 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 1
16 | FLANGES
16.1 | Dia. 3" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31-D01-05 | NOS | 22 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 22 | 0
16.2 | Dia. 2" ASTM A105 CL150 RF WN ASME-B16.5 SCH80 P20B31-D01-07 | NOS | 19 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 19 | 0
16.3 | Dia. 1 1/2" ASTM A105 CL150 RF SW ASME-B16.5 SCH80 P20B31-D02-07 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
16.4 | Dia. 1" ASTM A105 CL150 RF SW ASME-B16.5 SCH80 P20B31-D02-07 | NOS | 18 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 10 | 8
16.5 | Dia. 1 1/4" ASTM A105 CL150 RF SW ASME-B16.5 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 1 | 1
16.6 | Dia. 4" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31-D01-05 | NOS | 23 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 23 | 0
16.7 | Dia. 2" ASTM A105 CL150 RF WN ASME-B16.5 SCH80 P20B31-D01-07 | NOS | 98 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 98 | 0
16.8 | Dia. 1" ASTM A105 CL150 RF SW ASME-B16.5 SCH160 P20B31-D02-11 | NOS | 12 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 12
16.9 | Dia. 1" ASTM A105 GALVANIZED CL150 RF THD ASME-B16.5 P20B31-F15 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 9 | 0
17 | BLIND FLANGES:
17.1 | Dia. 3" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
17.2 | Dia. 2" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
17.3 | Dia. 4" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
17.4 | Dia. 2" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 8 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 8 | 0
17.5 | Dia. 1" ASTM A105 GALVANIZED CL150 RF ASME-B16.5 P22B31-F05 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 0
18 | GASKET
18.1 | Dia. 3" 316SS FLEXITE SUPER STYLE CG SPIRAL WOUND (PINK STRIPE) OR EQUAL CL150 1/8" THICK. ASME-B16.20 P27U31-D02 | NOS | 23 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 23
18.2 | Dia. 2" 316SS FLEXITE SUPER STYLE CG SPIRAL WOUND (PINK STRIPE) OR EQUAL CL150 1/8" THICK. ASME-B16.20 P27U31-D02 | NOS | 15 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 15
18.3 | Dia. 1 1/2" 316SS FLEXITE SUPER STYLE CG SPIRAL WOUND (PINK STRIPE) OR EQUAL CL150 1/8" THICK. ASME-B16.20 P27U31-D02 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 2
18.4 | Dia. 1" 316SS FLEXITE SUPER STYLE CG SPIRAL WOUND (PINK STRIPE) OR EQUAL CL150 1/8" THICK. ASME-B16.20 P27U31-D02 | NOS | 15 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 15
18.5 | Dia. 4" 316 SS FLEXICARB(FLEXIBLE GRAPHITE FILL) STYLE CGI SPIRAL WOUND (GREY-STRIPE) CL150 1/8" THICK. ASMEB16.20 P27U31-D01 | NOS | 24 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 24
18.6 | Dia. 2" 316 SS FLEXICARB(FLEXIBLE GRAPHITE FILL) STYLE CGI SPIRAL WOUND (GREY-STRIPE) CL150 1/8" THICK. ASMEB16.20 P27U31-D01 | NOS | 96 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 96
18.7 | Dia. 1" 316 SS FLEXICARB(FLEXIBLE GRAPHITE FILL) STYLE CGI SPIRAL WOUND (GREY-STRIPE) CL150 1/8" THICK. ASMEB16.20 P27U31-D01 | NOS | 12 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 12
18.8 | Dia. 1" 316SS FLEXITE SUPER STYLE CG SPIRAL WOUND (PINK STRIPE) OR EQUAL CL150 1/8" THICK. ASME-B16.20 P27U31-D02 | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 5
19 | STUD BOLT
19.1 | 5/8" x 90mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 92 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 92 | 0
19.2 | 5/8" x 85mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 60 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 60 | 0
19.3 | 1/2" x 80mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
19.4 | 1/2" x 65mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 40 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 124 | -84
19.5 | 5/8" x 100mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 24 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 20 | 4
19.6 | 5/8" x 95mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 20 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 20 | 0
19.7 | 5/8" x 90mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 144 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 144 | 0
19.8 | 5/8" x 85mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 344 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 209 | 135
19.9 | 1/2" x 65mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 68 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 68
19.1 | 1/2" x 65mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 20 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 20
20 | PLUG
20.1 | Dia. 3/4" ASTM A105 ROUND HEAD NPT ASME-B16.11 P16B00-A02 | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 4 | 0
20.2 | Dia. 1/2" ASTM A105 ROUND HEAD NPT ASME-B16.11 P16B00-A02 | NOS | 9 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 9 | 0
20.3 | Dia. 3/4" ASTM A105 ROUND HEAD NPT ASME-B16.11 P16B00-A02 | NOS | 23 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 23 | 0
20.4 | Dia. 1/2" ASTM A105 ROUND HEAD NPT ASME-B16.11 P16B00-A02 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
20.5 | Dia. 3/4" ASTM A105 GALVANIZED ROUND HEAD NPT ASMEB16.11 P16B00-A04 | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 21-Oct-18 6-Dec-18 | 6 | -3
21 | SPECTACLE BLIND
21.1 | Dia. 4" SPECTACLE BLIND RF 150# | NOS | 3 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 3 | 0
21.2 | Dia. 2" SPECTACLE BLIND RF 150# | NOS | 5 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 5 | 0
22 | COUPLING
22.1 | Dia. 1/2" ASTM A105 CL3000 SW-THR NPT ASME-B16.11 P12B11-A02 | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 2 | 0
22.2 | Dia. 1" ASTM A105 GALVANIZED CL3000 THD/THD ASME-B16.11 P12B11-A10 | NOS | 7 | Done | Done | Done | Done | Done | 2018-08-20 | 2018-10-21 | 7 | 0
23 | INSULATION KIT
23.1 | Dia. 2" 150# INSULATION KIT CONTAINING GASKET, NUTS, WASHERS, AND COATED BOLTS | NOS | 4 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 4
23.2 | Dia. 1 1/4"" 150# INSULATION KIT CONTAINING GASKET, NUTS, WASHERS, AND COATED BOLTS | NOS | 2 | Done | Done | Done | Done | Done | 2018-08-20 |  |  | 2
B | Fire Water Piping
1 | Pipes
1.1 | Dia.10" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A30-05 | Meter | 2 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 6 | -4
1.2 | Dia.8" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A30-05 | Meter | 244 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 192 | 52 |  | BOQ revised on 03-November-2018
1.3 | Dia.4" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A30-05 | Meter | 342 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 306 | 36 |  | BOQ revised on 03-November-2018
1.4 | Dia.3" ASTM A106 GR.B SMLS BE ASME-B36.10M SCH40 P01A01-A30-05 | Meter | 289 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-12-06 | 288 | 1 |  | BOQ revised on 03-November-2018
1.5 | Dia.3/4" ASTM A106 GR.B SMLS PE ASME-B36.10M SCH80 P01A01- A32-07 | Meter | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 1 | 0
2 | 90 ELBOW
2.1 | Dia. 8" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASME-B16.9 SCH40 P02A01-A01-05 | NOS | 8 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 8 | 0 |  | BOQ revised on 03-November-2018
2.2 | Dia. 4" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASME-B16.9 SCH40 P02A01-A01-05 | NOS | 20 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 22 | -2 |  | BOQ revised on 03-November-2018
2.3 | Dia. 3" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASME-B16.9 SCH40 P02A01-A01-05 | NOS | 30 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 28 | 2 |  | BOQ revised on 03-November-2018
3 | 45 ELBOW:
3.1 | Dia. 10" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASME-B16.9 SCH40 P03A01-A01-05 | NOS | 2 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 2 | 0
3.2 | Dia. 8" ASTM A234 GR.WPB SMLS LONG RADIUS BW ASME-B16.9 SCH40 P03A01-A01-05 | NOS | 8 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 8 | 0 |  | BOQ revised on 03-November-2018
4 | EQUAL TEE
4.1 | Dia. 8" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 P04A01- A01-05 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 1 | 0
4.2 | Dia. 3" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 P04A01- A01-05 | NOS | 5 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 3 | 2 |  | BOQ revised on 03-November-2018
5 | Reducing TEE
5.1 | Dia. 8" X 4" ASTM A234 GR.WPB SMLS BW ASME-B16.9 SCH40 (L) X SCH40 (S) P05A01-A01-0505 | NOS | 2 | Done | Done | Done | Done | Done | - | 2018-12-21 | 2 | 0 |  | New added in revised BOQ on 03-November-2018
6 | WELDOLET
6.1 | Dia. 10"x4" ASTM A105 BW WELDOLET MSS-SP97 SCH40 P13B00-D01-05 | NOS | 3 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 3 | 0
6.2 | Dia. 8"x3" ASTM A105 BW WELDOLET MSS-SP97 SCH40 P13B00-D01-05 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 1 | 0
7 | SOCKOLET
7.1 | Dia. 4"x3/4" ASTM A105 CL3000 SOCKOLET SW MSS-SP97 P13B11- D01 | NOS | 3 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 3
8 | BALL VALVE
8.1 | Dia. 3/4" BODY:ASTM A105 TRIM/BALL:13%CR FLOATING BALL REINPTFEANTISTATIC FIRESAFE BS6755 END ENTRY CL800 WRENCH OPERATED SW-NPT BS 5351 P33B1H-D02 | NOS | 3 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 3
9 | GATE VALVE
9.1 | Dia. 8" BODY: ASTM A216 GR.WCB TRIM:13% CR D&S: STL CL150 BB-BG-OS&Y STD-PORT FLANGED RF API600 P30C1B-A09 | NOS | 2 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 2 | 0 |  | BOQ revised on 03-November-2018
9.2 | Dia. 4" BODY: ASTM A216 GR.WCB TRIM:13% CR D&S: STL CL150 BB-BG-OS&Y STD-PORT FLANGED RF API600 P30C1B-A09 | NOS | 3 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 3 | 0
9.3 | Dia. 3" BODY: ASTM A216 GR.WCB TRIM:13% CR D&S: STL CL150 BB-BG-OS&Y STD-PORT FLANGED RF API600 P30C1B-A09 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 3 | -2 |  | BOQ revised on 03-November-2018
10 | Y-TYPE STRAINER
10.1 | Dia. 8" Y-TYPE STRAINER, ASTM A216 GR.WCB, FLANGED RF, CL150 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 1
11 | FLANGES
11.1 | Dia. 10" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31- D01-05 | NOS | 2 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 2 | 0
11.2 | Dia. 8" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31- D01-05 | NOS | 7 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 7 | 0 |  | BOQ revised on 03-November-2018
11.3 | Dia. 4" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31- D01-05 | NOS | 23 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 23 | 0
11.4 | Dia. 3" ASTM A105 CL150 RF WN ASME-B16.5 SCH40 P20B31- D01-05 | NOS | 26 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-12-06 | 22 | 4 |  | BOQ revised on 03-November-2018
12 | BLIND FLANGES
12.1 | Dia. 10" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 1 | 0
12.2 | Dia. 3" ASTM A105 CL150 RF ASME-B16.5 P22B31-D01 | NOS | 1 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 1 | 0
13 | GASKET
13.1 | Dia. 10" COMPRESSED ,NON ASBESTOS FLAT RING CL150 1/16" THICK ASME B16.21 P27R31-A05 | NOS | 2 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 2
13.2 | Dia. 8" COMPRESSED ,NON ASBESTOS FLAT RING CL150 1/16" THICK ASME B16.21 P27R31-A05 | NOS | 8 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 8 |  | BOQ revised on 03-November-2018
13.3 | Dia. 4" COMPRESSED ,NON ASBESTOS FLAT RING CL150 1/16" THICK ASME B16.21 P27R31-A05 | NOS | 16 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 16
13.3 | Dia. 3" COMPRESSED ,NON ASBESTOS FLAT RING CL150 1/16" THICK ASME B16.21 P27R31-A05 | NOS | 17 | Done | Done | Done | Done | Done | 2018-09-15 |  |  | 17 |  | BOQ revised on 03-November-2018
14 | STUD BOLT | [10 empty] | 0
14.1 | 7/8" x 115mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 24 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 24 | 0
14.2 | 3/4" x 110mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 64 | Done | Done | Done | Done | Done | 2018-09-15 | 21-Oct-18 21-Dec-18 | 64 | 0 |  | BOQ revised on 03-November-2018
14.3 | 5/8" x 90mm LONG ASTM A193 GR.B7 CAD PLT/A194 GR.2H CAD PLT. STUD BOLT WITH 2 HEAVY-HEX-NUT UNIFIED THREAD ASMEB1.1 P29F09-A11 | NOS | 196 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 212 | -16 |  | BOQ revised on 03-November-2018
15 | PLUG | [10 empty] | 0
15.1 | Dia. 1/2" ASTM A105 ROUND HEAD NPT ASME-B16.11 P16B00-A02 | NOS | 3 | Done | Done | Done | Done | Done | 2018-09-15 | 2018-10-21 | 2 | 1
16 | DELUGE VALVE | [10 empty] | 0
16.1 | Dia. 3" DELUGE VALVE SEE DATA SHEET | NOS | 1 | [8 empty] | 1 |  | New added in revised BOQ on 03-November-2018
C | Foam System
1 | Fixed Foam System 01 no. Centralized foam proportioning and induction system comprises of 01 no. foam concentrate tank having capacity 1700 liters, 01 nos. flow inductors of capacity 800 LPM @ 3 barg (min). | Nos | 1 | [8 empty] | 1 |  | Vendor Conformation is still awaited from client.
2 | Foam Pourers 03 no. tank top pourer with foam chamber and foam deflector plate. | Nos | 3 | [8 empty] | 3 |  | Vendor Conformation is still awaited from client.
3 | Foam and Water dual fire hydrant monitor 02 nos. with. AFFF foam concentrate of 5 gallons pail for each fire Hydrant monitor. | Nos | 2 | [8 empty] | 2 |  | Vendor Conformation is still awaited from client.
4 | Fire Hose Cabinets 02 Nos. with 2-1/2" dia - 100 ft. long hose reel equip with instantanous couplings at both ends and nozzle. | Nos | 2 | [8 empty] | 2 |  | Vendor Conformation is still awaited from client.
D | Pipe Supports and Cross Overs Structure | [10 empty] | 0
1 | Pipe Supports | [10 empty] | 0
1.1 | H-Beam 152 X 152 X 30 | Meter | 59 | [7 empty] | 57.58 | 1.42
1.1 | H-Beam 152 X 152 X 23 | Meter | 29 | [8 empty] | 29
1.2 | M.S Angles 80 X 80 X 10 mm | Meter | 55 | [8 empty] | 55
1.3 | Base Plates 300 X 300 X 15 mm | Nos | 36 | [8 empty] | 36
1.3 | Base Plates 250 X 250 X 12mm | Nos | 16 | [8 empty] | 16
1.4 | U Clamps Ø20 with 04 No. Nuts & Washers (114mm) | Nos | 25 | [8 empty] | 25
1.5 | U Clamps Ø20 with 04 No. Nuts & Washers (33mm) | Nos | 25 | [8 empty] | 25
1.6 | Pipe Ø 3" LEN. 120mm | Meter | 2 | [8 empty] | 2 |  | Available
1.7 | Bolt Ø 1" LEN. 203mm with 2 Nuts | Nos | 12 | [8 empty] | 12
2 | Cross Overs
2.1 | C-Chanel (HD) 152 X 76 X 17.88 mm | Meter | 60 | Done | Done | Done | Done | Done |  | 2018-12-25 | 6.72 | 53.28 |  | Re-check required
2.2 | Railing Pipe (2" For Detail See Drawing) | Meter | 124 | [8 empty] | 124
2.3 | Chequered Plate 2270 X 1090 X 6mm | Nos | 2 | Done | Done | Done | Done | Done |  | 2018-12-25 | 2 | 0
2.4 | Chequered Plate 930 X 1065 X 6mm | Nos | 1 | Done | Done | Done | Done | Done |  | 2018-12-25 | 1 | 0
2.5 | Chequered Plate 870 X 1090 X 6mm | Nos | 1 | Done | Done | Done | Done | Done |  | 2018-12-25 | 1 | 0
2.6 | Chequered Plate 305 X 940 X 6mm | Nos | 32 | Done | Done | Done | Done | Done |  | 2018-12-25 | 32 | 0
2.6 | MS Base Plate 175 X 275 X 16mm | Nos | 16 | [8 empty] | 16
E | Tanks Material
1 | PLATES | [10 empty] | 0
1.1 | 8mm x 1500 x 8000(754/Nos) | Nos | 114 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 114 | 0
1.2 | 08mm x 1500 x 6000(566kg/Nos) | Nos | 18 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 18 | 0
1.3 | 05mm x 1500 x 8000(471kg/Nos) | Nos | 9 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 9 | 0
1.4 | 10mm x 1500 x 8000(942kg/Nos) | Nos | 45 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 45 | 0
1.5 | 10mm x 1500 x 6000(707kg/Nos) | Nos | 12 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 12 | 0
1.6 | 06mm x 1500 x 8000(566kg/Nos) | Nos | 6 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 6 | 0
1.7 | 15/16mm x 1000 x 3000(353kg/Nos) | Nos | 3 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 3 | 0
1.8 | 16mm x 1000 x 1000(126kg/Nos) | Nos | 1 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 1 | 0
1.9 | 19/20mm x 1000 x 1000(157kg/Nos) | Nos | 3 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 3 | 0
1.1 | 25mm x 1500 x 6000 (1767Kg/Nos) | Nos | 1 | Done | Done | Done | Done | Done |  | 2018-12-06 | 1 | 0
1.11 | 16 X 1220 X 2700mm | Nos | 3 | Done | Done | Done | Done | Done |  | 2018-12-17 | 3 | 0
1.12 | 12 X 1225 X 1230mm | Nos | 6 | Done | Done | Done | Done | Done |  | 2018-12-17 | 6 | 0
2 | STRUCTURE | [10 empty] | 0
2.1 | M.S Channel 255 X 85 X 10 mm ( 37.9 kg/m) | Meter | 129 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 129 | 0
2.2 | M.S Channel 150 X 75 X 08 mm (16.0 kg/m) | Meter | 222 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 221.6 | 0.4
2.3 | M.S Channel 150 X 75 X 08 mm (3230 mm LG.) | Nos | 9 | [8 empty] | 9
2.3 | M.S Channel 100 x 50mm x 8mm 10.65 kg/m | Meter | 22 | Done | Done | Done | Done | Done | 2018-08-01 | 12-Oct-18 25-Dec-18 | 22.26 | -0.26
2.4 | M.S Channel 75 X 40 X 5 mm (8.77 kg/m) | Meter | 150 | Done | Done | Done | Done | Done | 2018-08-01 | 12-Oct-18 25-Dec-18 | 38.975 | 111.025
2.5 | M.S Angle 50 x 50 x 6mm(4.71kg/m) | Meter | 124 | Done | Done | Done | Done | Done | 2018-08-01 | 12-Oct-18 25-Dec-18 | 23.94 | 100.06
2.6 | M.S Angle 65 X 65 X 5 mm(6.83kg/m) | Meter | 46 | Done | Done | Done | Done | Done | 2018-08-01 | 12-Oct-18 25-Dec-18 | 30.48 | 15.52
2.7 | M.S Angle 100 X 100 x 09 mm(14.7kg/m) | Meter | 102 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 140.8 | -38.8
2.8 | M.S Angle 120 x 120 x 10mm(18.2kg/m) | Meter | 27 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-10-12 | 34 | -7
2.9 | M.S Angle 150 x 150 x 10mm(23kg/m) (6200 LG.) | Nos | 23 | Done | Done | Done | Done | Done | 2018-08-01 | 2018-12-06 | 23 | 0
2.1 | M.S Angle 65 X 65 X 8 mm | Meter | 252 | Done | Done | Done | Done | Done | - | 2018-12-06 | 252 | 0
2.11 | Flat Bar 50 X 5mm | Meter | 14 | Done | Done | Done | Done | Remaining |  |  |  | 14
2.12 | Hex. Head Bolt M20 X 60mm LG. with Nut & Washer ISO 898 Gr.8.8 / ISO 4032 Gr.10 | Nos | 660 | Done | Done | Done | Done | Done | - | 2018-12-16 | 660 | 0 |  | Note: All carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
3 | Stair Case and Railing
3.1 | M.S PLATES 6mm x 1500 x 4000 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3 |  | Hold
3.2 | M.S PLATES 10mm x 1500 x6000 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3 |  | Hold
3.3 | M.S CHANNELS 6"X3" (18.4kg/m) | Meter | 45 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 45
3.4 | M.S ANGLES 50 x 50 x 6mm(4.71kg/m) | Meter | 228 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 228
3.5 | M.S ANGLES 75 x 75 x 8mm(9.2kg/m) | Meter | 45 | Done | Done | Done | Done | Done | 2018-11-15 |  | 48.94 | -3.94
3.6 | Pipe(Hand rail) 1 1/2" Sch.40 (4.06kg/m) | Meter | 220 | Done | Done | Done | Done | Remaining |  |  |  | 220
3.7 | Flat Bar(For Toe Bar) 80X5mm(3.15kg/m) | Meter | 120 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 120
3.8 | Flat Bar(For knee Bar) 40X5mm (1.55kg/m) | Meter | 231 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 231
3.9 | Stair Steps See detail in drawing(10kg/nos) | Nos | 126 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 126
3.1 | Grating For platform See detail in drawing(32kg/no's) | Nos | 9 | Done | Done | Done | Done | Done | 2018-11-15 |  |  | 9
3.11 | End Cap 1 1/2" Sch. 40(0.5kg/nos) | Nos | 18 | Done | Done | Done | Done | Remaining |  |  |  | 18
3.12 | Bolts & Washers Hex. Head Bolt M16x60 LG. with W/Nut & washer | Nos | 430 | Done | Done | Done | Done | Remaining |  |  |  | 430
3.13 | Anchor Bolts M20 X 300mm Long With 2 Nut & Washers | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4 | NOZZEL MATERIAL
4.1 | Pipe 2" Sch.80 A 106-GR.B | Meter | 210 | Done | Done | Done | Done | Remaining |  |  |  | 210
4.2 | Pipe 3" Sch.40 A 106-GR.B | Meter | 23 | Done | Done | Done | Done | Remaining |  |  |  | 23
4.3 | Pipe NB 2" Sch.80 A 106-GR.B | Meter | 110 | Done | Done | Done | Done | Remaining |  |  |  | 110
4.5 | Pipe NB 4" Sch.80 A 106-GR.B | Meter | 20 | Done | Done | Done | Done | Remaining |  |  |  | 20
4.6333 | Pipe NPS 1-1/4" Sch.80 A 106-GR.B | Meter | 6.5 | Done | Done | Done | Done | Remaining |  |  |  | 6.5
4.7833 | Pipe NPS 2" Sch.160 A 106-GR.B | Meter | 25 | Done | Done | Done | Done | Remaining |  |  |  | 25
4.9333 | Pipe NPS 20" X 10mm Thk. A 106-GR.B | Meter | 1 | Done | Done | Done | Done | Remaining |  |  |  | 1
4.1 | Pipe NPS 2-1/2" Sch.80 A 106-GR.B | Meter | 4 | Done | Done | Done | Done | Remaining |  |  |  | 4
4.11 | Pipe NPS 3" Sch.40 A 106-GR.B | Meter | 1 | Done | Done | Done | Done | Remaining |  |  |  | 1
4.12 | Pipe NPS 4" Sch.160 A 106-GR.B | Meter | 54 | Done | Done | Done | Done | Remaining |  |  |  | 54
4.13 | Pipe NPS 4" Sch.80 A 106-GR.B | Meter | 14 | Done | Done | Done | Done | Remaining |  |  |  | 14
4.14 | Pipe NPS 6" Sch.160 A 106-GR.B | Meter | 30 | Done | Done | Done | Done | Remaining |  |  |  | 30
4.15 | Elbow 900 LR 2" (TRIM) Sch. 80 A 234-WPB | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15
4.16 | Elbow 900 LR 3" Sch. 40 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.17 | Elbow 450 LR 3" Sch. 40 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.18 | Elbow 900 LR NB 2" Sch. 80 A 234-WPB | Nos | 30 | Done | Done | Done | Done | Remaining |  |  |  | 30
4.19 | Elbow 450 LR NB 3" Sch. 80 A 234-WPB | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.2 | Elbow 900 LR NB 4" Sch. 80 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.21 | Elbow 900 NPS 2" LR BW Sch. 160 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.22 | Elbow 900 NPS 4" LR BW Sch. 80 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.23 | Equal Tee 3" Sch.40 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.24 | Equal Tee 2" Sch.80 A 234-WPB | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.25 | Flange 3" # 150 WNRF Sch.40 A 105 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.26 | Flange NBP 2" # 150 WNRF A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.27 | Flange NPS 2" # 150 SORF Sch.40 A 105 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.28 | Flange NPS 2" # 150 WNRF Sch.80 A 105 | Nos | 24 | Done | Done | Done | Done | Remaining |  |  |  | 24
4.29 | Flange NPS 2" # 150 WNRF Sch.160 A 105 | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15
4.3 | Flange NPS 20" # 150 WNRF Sch.160 A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.31 | Flange NPS 3" # 150 WNRF Sch.80 A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.32 | Flange NPS 4" # 150 WNRF Sch.80 A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.33 | Flange NPS 4" # 150 WNRF Sch.160 A 105 | Nos | 9 | Done | Done | Done | Done | Remaining |  |  |  | 9
4.34 | Flange NPS 4" # 150 SORF Sch.160 A 105 | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15
4.35 | Flange NPS 6" # 150 SORF Sch.160 A 105 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.36 | Flange NPS 6" # 150 WNRF Sch.160 A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.37 | Flange O.D 762mm X I.D 623.6mm X 16mm Thk. SS-400 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.38 | Flange O.D 820mm X I.D 633mm X 16mm Thk. SS-400 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.39 | Blind Flange NPS 6" # 150 WNRF A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.4 | Reducer ECC. NB 4" X NB 3" Sch.80 A 234-WPB | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.41 | Reducer Concentric 3" X 2" Sch.80 A 234-WPB | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.42 | Sockolet 2" X 1/2" # 3000 A 105 | Nos | 105 | Done | Done | Done | Done | Remaining |  |  |  | 105
4.43 | Spray Nozzle 1/2" NPT | Nos | 105 | Done | Done | Done | Done | Remaining |  |  |  | 105
4.44 | Half Coupling Threaded NPS 1.5" # 3000 A 105 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.45 | Gasket 1.5mm Thk. Graphite | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.46 | Gasket 3mm Thk. Fiber Sheet / Non Asbestos | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.47 | Gasket NPS 4" Spiral Wound SS316L (Graphite) | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.48 | Gasket NPS 6" X 3mm Thk. Graphite / Gorlock | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.49 | Gasket O.D 127mm X I.D 92mm X 3mm Thk. Graphite | Nos | 21 | Done | Done | Done | Done | Remaining |  |  |  | 21
4.5 | Gasket O.D 227mm X I.D 114mm X 3mm Thk. Graphite | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.51 | Gasket O.D 735mm X I.D 600mm X 3mm Thk. Graphite Gorlock | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.52 | Gasket O.D 750mm X I.D 635mm X 1.5mm Thk. Graphite / Gorlock | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.53 | Gasket O.D 762mm X I.D 629 X 1.5mm Thk. | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.54 | Crosby U-Bolt Wire Rope Clips 1/2" | Nos | 76 | Done | Done | Done | Done | Remaining |  |  |  | 76
4.55 | Eye Bolt 1" UNC with 2 Nuts & Washers | Nos | 5 | Done | Done | Done | Done | Remaining |  |  |  | 5
4.56 | Eye Bolt M16 X 140mm LG. | Nos | 5 | Done | Done | Done | Done | Remaining |  |  |  | 5
4.57 | Handle Rod Ø 10mm X 300mm LG. A-36 | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15
4.58 | Hex. Head Bolt 3/4" UNC X 60 LG. with Hex. Nut A 193 Gr.B7 / A 194 Gr.2H | Nos | 120 | Done | Done | Done | Done | Remaining |  |  |  | 120
4.59 | Hex Head Bolt M12 X 64 LG. with Hex Nuts | Nos | 45 | Done | Done | Done | Done | Remaining |  |  |  | 45 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.6 | Hex Head Bolt M12 X 75 LG with Nut / Washer A 193-B7 / A 194-2 H | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.61 | Hex Head Bolt M12 X 75 LG with Nut / Washer A-36 | Nos | 8 | Done | Done | Done | Done | Remaining |  |  |  | 8
4.62 | Hex Head Bolt M16 X 50 LG. with 2-HEX Nuts A 193 Gr.B7 / A 194 Gr.2H | Nos | 30 | Done | Done | Done | Done | Remaining |  |  |  | 30 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.63 | Hex Head Bolt M16 X 50mm LG. with Nut & Washer A 193 Gr.B7 / A 194 Gr.2H | Nos | 66 | Done | Done | Done | Done | Remaining |  |  |  | 66 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.64 | Hex Head Bolt M16 X 64 LG. with Hex Nuts | Nos | 60 | Done | Done | Done | Done | Remaining |  |  |  | 60 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.65 | Hex. Head Bolt M16 X 65mm LG. with Nut & Washer A 193 Gr.B7 / A 194 Gr.2H | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.66 | Hex. Head Bolt M20 X 65 LG. with Nut & Washer A 193 Gr.B7 / A 194 Gr.2H | Nos | 90 | Done | Done | Done | Done | Remaining |  |  |  | 90
4.67 | Hex. Head Bolt M20 X 70 LG. with Nut / Washer A 193 Gr.B7 / A 194 Gr.2H | Nos | 15 | Done | Done | Done | Done | Remaining |  |  |  | 15 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.68 | Hex. Nut & STD. Cut Washer M16 A 194-2H | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.69 | Lug 50mm X 40mm X 8mm Thk. A-36 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.7 | Rod Ø 10mm X 100mm LG. A-36 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6
4.71 | Rod Ø 16mm X 145mm LG. A-36 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.72 | Rope Ø 1/2" | Meter | 51 | Done | Done | Done | Done | Remaining |  |  |  | 51
4.73 | Stud Bolt M16 X 90 LG. with 2-HEX Nuts A-193-B7 / A194-2H | Nos | 24 | Done | Done | Done | Done | Remaining |  |  |  | 24 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.74 | Stud Bolt M16 X 85 LG. with 2 Nuts A-193-B7 | Nos | 24 | Done | Done | Done | Done | Remaining |  |  |  | 24
4.75 | Stud Bolt M16 X 95 LG. with 2 Nuts A-193-B7 | Nos | 12 | Done | Done | Done | Done | Remaining |  |  |  | 12
4.76 | Stud Bolt M16 X 85 LG. with 2 Nuts A-193-B7 / A 194-2 H | Nos | 48 | Done | Done | Done | Done | Remaining |  |  |  | 48 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.77 | Stud Bolt M20 X 105 LG. with 2 Hex Nuts A-193-B7 / A 194-2 H | Nos | 48 | Done | Done | Done | Done | Remaining |  |  |  | 48 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.78 | Stud Bolt M16 X 85 LG. with 2 Nuts A-193-B7 | Nos | 36 | Done | Done | Done | Done | Remaining |  |  |  | 36
4.79 | U-Bolts with 4 Nuts For Pipe Ø 2" A-307 | Nos | 175 | Done | Done | Done | Done | Remaining |  |  |  | 175
4.8 | U-Bolts with 4 Nuts For Pipe Ø 3" A-307 | Nos | 12 | Done | Done | Done | Done | Remaining |  |  |  | 12
4.81 | U-Bolts with 4 Nuts For Pipe Ø 4" A-307 | Nos | 12 | Done | Done | Done | Done | Remaining |  |  |  | 12
4.82 | U-Bolts with 4 Nuts M12 X 370 LG. A 193-B7 / A 194-2 H | Nos | 12 | Done | Done | Done | Done | Remaining |  |  |  | 12
4.83 | U-Bolts with 4 Nuts M12 X 230 LG. A 193-B7 | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.84 | U-Bolts with 4 Nuts M16 A 193-B7 / A 194-2 H | Nos | 6 | Done | Done | Done | Done | Remaining |  |  |  | 6 |  | These Carbon steel Bolts, Washers and Nuts shall be Hot Dip Galvanized.
4.85 | Vacuum Relief Vent Model 120 NPS 4" | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
4.86 | Emergency Vent Shand & Gurs Model 94210 | Nos | 3 | Done | Done | Done | Done | Remaining |  |  |  | 3
Electrical & Instrumentation
A | Electrical
1 | Lighting:
1.1 | Flourescent lights ( 2 x 36 Watt) | Nos. | 15 | Done | Done | Done | Victor | In process | 2018-12-01 |  |  |  | 6-8 weeks
1.2 | Lighting junction Box | Nos. | 15 | Done | Done | Done | Hawke | In process | 2018-12-01
1.3 | Cable Glands |  |  | Done | Done | Done | Hawke | In process | 2018-12-01
2 | Power Cables :
i | Power Cable 2 Core CU/XLPE/SWA/PVC 2.5 mm² | Meter | 120 | Done | Done | Done | Pakistan Cable | In process | 2018-11-01 |  |  |  | 3-4 Weeks
3 | Earthing Material :
i | Bare stranded Copper Conductor size 70 mm² . | Meter | 360 | Done | Done | Done | Pakistan Cable | In process | 2018-11-01 |  |  |  | 3-4 Weeks
ii | Misc. Earthing Material like Earth Rod etc. | Job | 1 | Done | Done | Done | Local Market | [5 empty] | 1 Week
B | Instrument
1 | Field Instruments:
i | Pressure Transmitter | Nos. | 1 | Done | Done | Done | Rosemount | Done
ii | Radar type Level Transmitter (Control & ESD) | Nos. | 6 | Done | Done | Done | Rosemount | Done
iii | Pressure Gauge | Nos. | 4 | Done | Done | Done | Nouva Fima | In process
iv | Temperature Gauge | Nos. | 3 | Done | Done | Done | Nouva Fima | In process
v | Differential pressure indicator | Nos. | 1 | Done | Done | Done | Nouva Fima | In process
vi | Self regulating Pressure Regulators. | Nos. | 6 | Done | Done | Done | Fisher
vii | Breather Valve(PVSV) | Nos. | 3 | Done | Done | Done | Elmac Technologies | In process
viii | Emergency relief Valve(ESV) | Nos. | 3 | Done | Done | Done | Elmac Technologies | In process
ix | Level Gauges LG-9501, LG-9503 & LG-9504 For Details See Data Sheets | Nos. | 3 |  |  |  | Varec
2 | Instrument Cables & Accessories
i | Instrument Cable 1 PAIR 1.5 mm² 60/120V, CU/PE/OSCR/PE/SWA/PVC | Meter | 760 | Done | Done | Done | Pakistan Cable/Leoni Kerpen | In process | 2018-11-01 |  |  |  | 5-6 Weeks
ii | Cable Glands | Nos. | 20 | Done | Done | Done | Hawke | In process | 2018-12-01 |  |  |  | 5 weeks
3 | Junction Box
i | instrument junction box for ESD and DCS | Nos. | 2 | Done | Done | Done | Hawke | In process | 2018-12-01 |  |  |  | 4-6weeks
5 | Cable Tary/Conduit
i | Hot Dipped Galvanized Ladder Type Cable tray of Size 100 mm x 50 mm | Meter | 150 | Done | Done | Done | Local Market | [5 empty] | 3 weeks
ii | GI Conduit Size 2" | Meter | 50 | Done | Done | Done | Local Market | [5 empty] | 1 week
5 | Stair Case Material For Dyke Wall (03 Nos)
5.1 | MS Pipe 1 1/2" (Railing Pipe) | Meter | 100 | [8 empty] | 100
5.2 | Embeded Plate 150 X 150 X 10 mm | Nos | 54 | [8 empty] | 0 |  | Available
5.3 | Hilti Bolts M12 | Nos | 118 | [8 empty] | 118
Legend:
Remaining
Please RE Check in PO
Added / Revised
Received / Completed
Not Required / Deleted
Available
Hold