## WBS – FROM EXCEL
SR.# | WBS SHORT NAME/CODE | PARENT WBS | WBS DESCRIPTION www.planningp6.com
Leave this row unfilled.
Project Initiation
Project Charter Development
Feasibility Study
Technical Feasibility
Economic Feasibility
Regulatory Compliance
Pre-Contract Activities
RFP/RFQ Preparation
Bid Evaluation
Contract Negotiation
Project Kickoff Meeting
Meeting Preparation
Meeting Conduct
Next Steps/ Schedule Basis Memorandum Singn
Project Planning
Requirements Gathering
Business Requirements Gathering
Technical Requirements Gathering
Data Center Design Requirements
Infrastructure Requirements
IT Systems Requirements
Operational Requirements
Regulatory and Compliance Requirements
Documentation and Approval
Risk Assessment
Risk Identification
Risk Assessment
Risk Response Planning
Risk Monitoring and Control
Risk Documentation and Reporting
Risk Closure
Resource Planning
Resource Acquisition and Onboarding
Resource Allocation and Assignment
Resource Management and Control
Resource Offboarding and Transition
Schedule Development
Create work breakdown structure (WBS
Define task dependencies
Estimate task durations
Develop project schedule
Identify critical path
Budget Planning
Budget Development
Gather Requirements
Identify Funding Sources
Estimate Costs
Allocate Resources
Prepare Budget Documents
Budget Approval
Submit Budget for Review
Address Feedback and Revisions
Obtain Final Approval
Design and Engineering
Architectural Design
Site Analysis and Zoning
Building Layout and Concept Design
Envelope Design
Interior Design
Accessibility and Code Compliance
Structural Design
Structural Analysis and Calculations
Foundation Design and Specifications
Structural Systems (e.g., steel, concrete)
Electrical Design
Electrical Power Distribution
Primary Distribution
Secondary Distribution
Emergency Power System (EPS)
Uninterruptible Power Supply (UPS)
Earthing and Grounding
Lighting Systems
Low-Voltage Systems
Mechanical Design
Concept development
Detailed design
Calculations
Drawings
Specifications
Fire Protection Design
Fire Suppression System Design
Fire Detection and Alarm System Design
Fire Extinguisher Placement
Fire Hydrant System Design
Security Design
Physical Security
Access Control Systems:
Perimeter Security:
Environmental Security:
Network Design
Network architecture selection
Network layout planning
Connectivity design
Redundancy and fault tolerance design
Procurement
Vendor Selection
Contract Negotiation
Material Procurement
Equipment Procurement
Construction
Site Preparation
Subsoil Investigation
Site Clearing and Grading
Utility Relocation
Temporary Site Facilities
Foundation Work
Foundation footing construction
Reinforced concrete foundation walls
Basement construction
Slab-on-grade foundation
Pile foundation (if applicable)
Structural Construction
Columns
Beams
Slabs
Walls
Roofs
Electrical Installation
Substation:
Medium Voltage (MV) Switchgear:
Low Voltage (LV) Switchgear:
Cable Trays and Conduits:
Power Cables:
Earthing System:
Emergency Power Supply (EPS):
Uninterruptible Power Supply (UPS):
Static Transfer Switches (STS):
Generator Set:
Power Distribution Units (PDUs):
Electrical Distribution Network:
Mechanical Installation
Plumbing
Water Supply
Sanitary Sewer
Storm Drain
Fire Protection
Plumbing Fixtures
HVAC Installation
Air Handling Units (AHUs)
Chillers
Cooling Towers
Ductwork
Piping
Controls
Fire Protection Installation
Fire Sprinkler System
Fire Alarm System
Smoke Detection System
Fire Extinguishers
Testing and Commissioning
System Testing
Integration Testing
Acceptance Testing
Commissioning
Handover and Operations
Project Closeout
Documentation
Training
Handover to Client
Operations and Maintenance
Project Closure
Final Documentation
Lessons Learned
Project Evaluation
PLANNING-P6
ONE SOLUTION FOR PROJECT MANAGEMENT/CONTROLS PROBLEMS

## WBS – FROM EXCEL (1)
SR.# | WBS SHORT NAME/CODE | PARENT WBS | WBS DESCRIPTION www.planningp6.com
1 | Leave this row unfilled.
2 | PI | 1 | Project Initiation
3 | 101 | 2 | Project Charter Development
4 | 102 | 2 | Feasibility Study
5 | 1021 | 4 | Technical Feasibility
6 | 1022 | 4 | Economic Feasibility
7 | 1023 | 4 | Regulatory Compliance
8 | 103 | 2 | Pre-Contract Activities
9 | 1031 | 8 | RFP/RFQ Preparation
10 | 1032 | 8 | Bid Evaluation
11 | 1033 | 8 | Contract Negotiation
12 | 104 | 2 | Project Kickoff Meeting
13 | 1041 | 12 | Meeting Preparation
14 | 1042 | 12 | Meeting Conduct
15 | 1043 | 12 | Next Steps/ Schedule Basis Memorandum Singn
16 | PP | 1 | Project Planning
17 | 201 | 16 | Requirements Gathering
18 | 2011 | 17 | Business Requirements Gathering
19 | 2012 | 17 | Technical Requirements Gathering
20 | 2013 | 17 | Data Center Design Requirements
21 | 2014 | 17 | Infrastructure Requirements
22 | 2015 | 17 | IT Systems Requirements
23 | 2016 | 17 | Operational Requirements
24 | 2017 | 17 | Regulatory and Compliance Requirements
25 | 2018 | 17 | Documentation and Approval
26 | 202 | 16 | Risk Assessment
27 | 2021 | 26 | Risk Identification
28 | 2022 | 26 | Risk Assessment
29 | 2023 | 26 | Risk Response Planning
30 | 2024 | 26 | Risk Monitoring and Control
31 | 2025 | 26 | Risk Documentation and Reporting
32 | 2026 | 26 | Risk Closure
33 | 203 | 16 | Resource Planning
34 | 2031 | 33 | Resource Acquisition and Onboarding
35 | 2032 | 33 | Resource Allocation and Assignment
36 | 2033 | 33 | Resource Management and Control
37 | 2034 | 33 | Resource Offboarding and Transition
38 | 204 | 16 | Schedule Development
39 | 2041 | 38 | Create work breakdown structure (WBS
40 | 2042 | 38 | Define task dependencies
41 | 2043 | 38 | Estimate task durations
42 | 2044 | 38 | Develop project schedule
43 | 2045 | 38 | Identify critical path
44 | 205 | 16 | Budget Planning
45 | 2051 | 44 | Budget Development
46 | 20511 | 45 | Gather Requirements
47 | 20512 | 45 | Identify Funding Sources
48 | 20513 | 45 | Estimate Costs
49 | 20514 | 45 | Allocate Resources
50 | 20515 | 45 | Prepare Budget Documents
51 | 2052 | 44 | Budget Approval
52 | 20521 | 51 | Submit Budget for Review
53 | 20522 | 51 | Address Feedback and Revisions
54 | 20523 | 51 | Obtain Final Approval
55 | DE | 1 | Design and Engineering
56 | 301 | 55 | Architectural Design
57 | 3011 | 56 | Site Analysis and Zoning
58 | 3012 | 56 | Building Layout and Concept Design
59 | 3013 | 56 | Envelope Design
60 | 3014 | 56 | Interior Design
61 | 3015 | 56 | Accessibility and Code Compliance
62 | 302 | 55 | Structural Design
63 | 3021 | 62 | Structural Analysis and Calculations
64 | 3022 | 62 | Foundation Design and Specifications
65 | 3023 | 62 | Structural Systems (e.g., steel, concrete)
66 | 303 | 55 | Electrical Design
67 | 3031 | 66 | Electrical Power Distribution
68 | 30311 | 67 | Primary Distribution
69 | 30312 | 67 | Secondary Distribution
70 | 3032 | 66 | Emergency Power System (EPS)
71 | 3033 | 66 | Uninterruptible Power Supply (UPS)
72 | 3034 | 66 | Earthing and Grounding
73 | 3035 | 66 | Lighting Systems
74 | 3036 | 66 | Low-Voltage Systems
75 | 304 | 55 | Mechanical Design
76 | 3041 | 75 | Concept development
77 | 3042 | 75 | Detailed design
78 | 3043 | 75 | Calculations
79 | 3044 | 75 | Drawings
80 | 3045 | 75 | Specifications
81 | 305 | 55 | Fire Protection Design
82 | 3051 | 81 | Fire Suppression System Design
83 | 3052 | 81 | Fire Detection and Alarm System Design
84 | 3053 | 81 | Fire Extinguisher Placement
85 | 3054 | 81 | Fire Hydrant System Design
86 | 306 | 55 | Security Design
87 | 3061 | 86 | Physical Security
88 | 3062 | 86 | Access Control Systems:
89 | 3063 | 86 | Perimeter Security:
90 | 3064 | 86 | Environmental Security:
91 | 307 | 55 | Network Design
92 | 3071 | 91 | Network architecture selection
93 | 3072 | 91 | Network layout planning
94 | 3073 | 91 | Connectivity design
95 | 3074 | 91 | Redundancy and fault tolerance design
96 | P | 1 | Procurement
97 | 401 | 96 | Vendor Selection
98 | 402 | 96 | Contract Negotiation
99 | 403 | 96 | Material Procurement
100 | 404 | 96 | Equipment Procurement
101 | C | 1 | Construction
102 | 501 | 101 | Site Preparation
103 | 5011 | 102 | Subsoil Investigation
104 | 5012 | 102 | Site Clearing and Grading
105 | 5013 | 102 | Utility Relocation
106 | 5014 | 102 | Temporary Site Facilities
107 | 502 | 101 | Foundation Work
108 | 5021 | 107 | Foundation footing construction
109 | 5022 | 107 | Reinforced concrete foundation walls
110 | 5023 | 107 | Basement construction
111 | 5024 | 107 | Slab-on-grade foundation
112 | 5025 | 107 | Pile foundation (if applicable)
113 | 503 | 101 | Structural Construction
114 | 5031 | 113 | Columns
115 | 5032 | 113 | Beams
116 | 5033 | 113 | Slabs
117 | 5034 | 113 | Walls
118 | 5035 | 113 | Roofs
119 | 504 | 101 | Electrical Installation
120 | 5041 | 119 | Substation:
121 | 5042 | 119 | Medium Voltage (MV) Switchgear:
122 | 5043 | 119 | Low Voltage (LV) Switchgear:
123 | 5044 | 119 | Cable Trays and Conduits:
124 | 5045 | 119 | Power Cables:
125 | 5046 | 119 | Earthing System:
126 | 5047 | 119 | Emergency Power Supply (EPS):
127 | 5048 | 119 | Uninterruptible Power Supply (UPS):
128 | 5049 | 119 | Static Transfer Switches (STS):
129 | 5050 | 119 | Generator Set:
130 | 5051 | 119 | Power Distribution Units (PDUs):
131 | 5052 | 119 | Electrical Distribution Network:
132 | 505 | 101 | Mechanical Installation
133 | 5051 | 132 | Plumbing
134 | 50511 | 133 | Water Supply
135 | 50512 | 133 | Sanitary Sewer
136 | 50513 | 133 | Storm Drain
137 | 50514 | 133 | Fire Protection
138 | 50515 | 133 | Plumbing Fixtures
139 | 5052 | 132 | HVAC Installation
140 | 50521 | 139 | Air Handling Units (AHUs)
141 | 50522 | 139 | Chillers
142 | 50523 | 139 | Cooling Towers
143 | 50524 | 139 | Ductwork
144 | 50525 | 139 | Piping
145 | 50526 | 139 | Controls
146 | 506 | 101 | Fire Protection Installation
147 | 5061 | 146 | Fire Sprinkler System
148 | 5062 | 146 | Fire Alarm System
149 | 5063 | 146 | Smoke Detection System
150 | 5064 | 146 | Fire Extinguishers
151 | 601 | 1 | Testing and Commissioning
152 | 6011 | 151 | System Testing
153 | 6012 | 151 | Integration Testing
154 | 6013 | 151 | Acceptance Testing
155 | 6014 | 151 | Commissioning
156 | 701 | 1 | Handover and Operations
157 | 7011 | 156 | Project Closeout
158 | 7012 | 156 | Documentation
159 | 7013 | 156 | Training
160 | 7014 | 156 | Handover to Client
161 | 7015 | 156 | Operations and Maintenance
162 | 801 | 1 | Project Closure
163 | 8011 | 162 | Final Documentation
164 | 8012 | 162 | Lessons Learned
165 | 8013 | 162 | Project Evaluation
PLANNING-P6
ONE SOLUTION FOR PROJECT MANAGEMENT/CONTROLS PROBLEMS