## PlNNING-P6 Look ahead
2026-01-01
Looak A Head Plan
Activity ID | Activity Name | Activity Status | Start | Finish
PP6-SPP-1170 | Steel Fixing For raft and Retaining Wall | Not Started | 2026-01-01 | 2026-01-05 | Will be started and completed
PP6-SPP-1190 | Pouring of Concrete in Raft and Retaining Wall | Not Started | 2026-01-03 | 2026-01-07 | Will be started and completed
PP6-SPP-1230 | Layout for Excavation of Outer Wall | Not Started | 2026-01-08 | 2026-01-08 | Will be started and completed
PP6-SPP-1240 | Excavation Work For Column | Not Started | 2026-01-09 | 2026-01-18 | Will be started and continued
PP6-SPP-1610 | Revised Beam+Side Beam | Not Started | 2026-01-04 | 2026-01-08 | Will be started and completed
PP6-SPP-1760 | Shuttering of Slab | In Progress | 26-Dec-25 A | 2026-01-02 | To be continued and completed
PP6-SPP-1770 | Load Brearing Wall | In Progress | 27-Dec-25 A | 2026-01-05 | To be continued and completed
PP6-SPP-1780 | RCC Lintels | Not Started | 2026-01-01 | 2026-01-05 | Will be started and completed
PP6-SPP-1790 | Shuttering of Beams and Slab | Not Started | 2026-01-06 | 2026-01-10 | Will be started and completed
PP6-SPP-1800 | Steel Fixing of Slab | Not Started | 2026-01-11 | 2026-01-15 | Will be started and completed
PP6-SPP-1920 | Pouring of concrete | In Progress | 31-Dec-25 A | 2026-01-03 | To be continued and completed
PP6-SPP-2380 | Internal Plaster(ceiling + Walls) | In Progress | 31-Dec-25 A | 2026-01-04 | To be continued and completed
PP6-SPP-2390 | Layout of Brick Ballast | Not Started | 2026-01-05 | 2026-01-06 | Will be started and completed
PP6-SPP-2395 | Plumbing and electrical work | Not Started | 2026-01-07 | 2026-01-08 | Will be started and completed
PP6-SPP-2400 | PCC work | Not Started | 2026-01-09 | 2026-01-11 | Will be started and completed
PP6-SPP-2480 | Tiles Work | Not Started | 2026-01-12 | 2026-01-16 | Will be started and continued
PP6-SPP-2580 | Coping of Wall | In Progress | 31-Dec-25 A | 2026-01-04 | To be continued and completed
PP6-SPP-2600 | Plinth Protection | Not Started | 2026-01-05 | 2026-01-09 | Will be started and completed
000
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-