## TASKRSRC
task_id | TASK__status_code | rsrc_id | role_id | acct_id | task__task_name | rsrc_type | target_qty | delete_record_flag
Activity ID | (*)Activity Status | Resource ID | Role ID | Cost Account ID | (*)Activity Name | (*)Resource Type | Budgeted Units(h) | Delete This Row
B1000 | Not Started | V-6 |  |  | Excavation | Material | 8700
B1060 | Not Started | V-6 |  |  | Backfilling | Material | 7740
B1010 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 6825
B1020 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 74250
B1040 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 13920
B1050 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 17760
B1070 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 8000
B1030 | Not Started | V-6 |  |  | Form Work | Material | 36550
B1080 | Not Started | V-6 |  |  | Bitumen Coating | Material | 17200
B1090 | Not Started | V-6 |  |  | Excavation | Material | 4350
B1150 | Not Started | V-6 |  |  | Backfilling | Material | 3870
B1100 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 3412.5
B1110 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 37125
B1130 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 6960
B1140 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 8880
B1160 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 4000
B1120 | Not Started | V-6 |  |  | Form Work | Material | 18275
B1170 | Not Started | V-6 |  |  | Bitumen Coating | Material | 8600
B1180 | Not Started | V-6 |  |  | Excavation | Material | 17400
B1240 | Not Started | V-6 |  |  | Backfilling | Material | 15480
B1190 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 13650
B1200 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 148500
B1220 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 27840
B1230 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 35520
B1250 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 16000
B1210 | Not Started | V-6 |  |  | Form Work | Material | 73100
B1260 | Not Started | V-6 |  |  | Bitumen Coating | Material | 34400
B1270 | Not Started | V-6 |  |  | Excavation | Material | 21750
B1330 | Not Started | V-6 |  |  | Backfilling | Material | 19350
B1280 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 17062.5
B1290 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 185625
B1310 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 34800
B1320 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 44400
B1340 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 20000
B1300 | Not Started | V-6 |  |  | Form Work | Material | 91375
B1350 | Not Started | V-6 |  |  | Bitumen Coating | Material | 43000
B1360 | Not Started | V-6 |  |  | Excavation | Material | 30450
B1420 | Not Started | V-6 |  |  | Backfilling | Material | 27090
B1370 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 23887.5
B1380 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 259875
B1400 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 48720
B1410 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 62160
B1430 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 28000
B1390 | Not Started | V-6 |  |  | Form Work | Material | 127925
B1440 | Not Started | V-6 |  |  | Bitumen Coating | Material | 60200
B1450 | Not Started | V-6 |  |  | Excavation | Material | 4350
B1510 | Not Started | V-6 |  |  | Backfilling | Material | 3870
B1460 | Not Started | V-6 |  |  | P.C.C Concrete 1:4:8 | Material | 3412.5
B1470 | Not Started | V-6 |  |  | Reinforcement 60 Grade | Material | 37125
B1490 | Not Started | V-6 |  |  | Footing Concrete R.C.C (C20) | Material | 6960
B1500 | Not Started | V-6 |  |  | Foundation beam R.C.C (C20) | Material | 8880
B1520 | Not Started | V-6 |  |  | Flooring R.C.C (C20) | Material | 4000
B1480 | Not Started | V-6 |  |  | Form Work | Material | 18275
B1530 | Not Started | V-6 |  |  | Bitumen Coating | Material | 8600

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd/MM/yyyy CurrencyFormat=Pakistani Rupee